## Recap
Code | Item | [6 empty] | Project cost summary
1 | Earthworks | LbM | EqM | Duration (d) | Cost | Workmen | Total$ | No. wkdays | 50
1.1 | Excavation | 0 | 1 | 12 | 13000 | 5 | 15150 | No. caldays | 61
1.2 | Gravel bedding | 0 | 1 | 2 | 950 | 3 | Total men | Ovhead/day | 500
1.3 | Backfill | 0 | 1 | 3 | 1200 | 3 | 11 | Total workmen | 77
[8 empty] | Direct cost | 81900
2 | Structural works | [6 empty] | Overhead cost | 30500
2.1 | Formwork | [6 empty] | Total | 112400
2.1.1 | Slab (one-half) |  |  | Duration (d) | Cost |  | Total$
2.1.1.1 | Fabricate | 0 | 1 | 1 | 1000 | 4 | 2500
2.1.1.2 | Erect | 0 | 1 | 1 | 500 | 4 | Total men
2.1.1.3 | Strip | 0 | 1 | 0.5 | 500 | 3 | 14
2.1.1.4 | Clean & repair | 0 | 1 | 0.5 | 500 | 3
2.1.2 | Wall (one-third) | [5 empty] | Total$
2.1.2.1 | Fabricate | 0 | 1 | 1 | 1500 | 6 | 3250
2.1.2.2 | Erect | 0 | 1 | 1 | 750 | 4 | Total men
2.1.2.3 | Strip | 0 | 1 | 0.5 | 500 | 3 | 16
2.1.2.4 | Clean & repair | 0 | 1 | 0.5 | 500 | 3
2.2 | Reinforcement
2.2.1 | Slab (one-half) |  |  | Duration (d) | Cost |  | Total$
2.2.1.1 | Fabricate | 0 | 1 | 2 | 2750 | 4 | 5500
2.2.1.2 | Assemble | 0 | 1 | 2 | 2750 | 6 | Total men
10
2.2.2 | Wall (one-third) | [5 empty] | Total$
2.2.2.1 | Fabricate | 0 | 1 | 3 | 3500 | 4 | 7000
2.2.2.2 | Assemble | 0 | 1 | 3 | 3500 | 6 | Total men
10
2.3 | Concreting
2.3.1 | Slab (one-half) |  |  | Duration (d) | Cost |  | Total$
2.3.1.1 | Pour | 0 | 1 | 0.5 | 3000 | 6 | 4000
2.3.1.2 | Finishing | 0 | 1 | 0.5 | 1000 | 3 | Total men
9
2.3.2 | Wall (one-third) | [5 empty] | Total$
2.3.2.1 | Pour | 0 | 1 | 0.5 | 3000 | 5 | 4000
2.3.2.2 | Finishing | 0 | 1 | 0.5 | 1000 | 2 | Total men
7

## Duration & Costs
Code | Item | Labour intensive |  |  | Eqpmnt intensive
1 | Earthworks | Duration (d) | Cost | Workers | Duration (d) | Cost | Workers
1.1 | Excavation | 19 | 10000 | 12 | 12 | 13000 | 5
1.2 | Gravel bedding | 2 | 700 | 8 | 2 | 950 | 3
1.3 | Backfill | 5 | 1000 | 5 | 3 | 1200 | 3
2 | Structural works
2.1 | Formwork
2.1.1 | Slab (one-half) | Duration (d) | Cost | Workers | Duration (d) | Cost | Workers
2.1.1.1 | Fabricate | 2 | 500 | 8 | 1 | 1000 | 4
2.1.1.2 | Erect | 1 | 500 | 6 | 1 | 500 | 4
2.1.1.3 | Strip | 0.5 | 500 | 4 | 0.5 | 500 | 3
2.1.1.4 | Clean & repair | 0.5 | 500 | 4 | 0.5 | 500 | 3
2.1.2 | Wall (one-third)
2.1.2.1 | Fabricate | 2 | 1250 | 12 | 1 | 1500 | 6
2.1.2.2 | Erect | 2 | 1000 | 10 | 1 | 750 | 4
2.1.2.3 | Strip | 1 | 750 | 5 | 0.5 | 500 | 3
2.1.2.4 | Clean & repair | 1 | 750 | 5 | 0.5 | 500 | 3
2.2 | Reinforcement
2.2.1 | Slab (one-half) | Duration (d) | Cost | Workers | Duration (d) | Cost | Workers
2.2.1.1 | Fabricate | 3 | 2500 | 6 | 2 | 2750 | 4
2.2.1.2 | Assemble | 3 | 2500 | 10 | 2 | 2750 | 6
2.2.2 | Wall (one-third)
2.2.2.1 | Fabricate | 4 | 4000 | 6 | 3 | 3500 | 4
2.2.2.2 | Assemble | 4 | 4000 | 12 | 3 | 3500 | 6
2.3 | Concreting
2.3.1 | Slab (one-half) | Duration (d) | Cost | Workers | Duration (d) | Cost | Workers
2.3.1.1 | Pour | 1 | 2500 | 10 | 0.5 | 3000 | 6
2.3.1.2 | Finishing | 1 | 1500 | 6 | 0.5 | 1000 | 3
2.3.2 | Wall (one-third)
2.3.2.1 | Pour | 1 | 3500 | 12 | 0.5 | 3000 | 5
2.3.2.2 | Finishing | 0.5 | 1250 | 2 | 0.5 | 1000 | 2

## Quantities
Code | Item | Quantity | Units
1 | Earthworks
1.1 | Excavation | 7300 | m3
1.2 | Gravel bedding | 185 | m3
1.3 | Backfill | 2800 | m3
2 | Structural works
2.1 | Formwork
2.1.1 | Slab (one-half) | 28 | m2
2.1.1.1 | Fabricate
2.1.1.2 | Erect
2.1.1.3 | Strip
2.1.1.4 | Clean & repair
2.1.2 | Wall (one-third) | 145 | m2
2.1.2.1 | Fabricate
2.1.2.2 | Erect
2.1.2.3 | Strip
2.1.2.4 | Clean & repair
2.2 | Reinforcement
2.2.1 | Slab (one-half) | 280 | kg
2.2.1.1 | Fabricate
2.2.1.2 | Assemble
2.2.2 | Wall (one-third) | 92 | kg
2.2.2.1 | Fabricate
2.2.2.2 | Assemble
2.3 | Concreting
2.3.1 | Slab (one-half) | 140 | m3
2.3.1.1 | Pour
2.3.1.2 | Finishing
2.3.2 | Wall (one-third) | 92 | m3
2.3.2.1 | Pour
2.3.2.2 | Finishing

## Bid Form
BID FORM
CE3161 Estimating and Scheduling Project
| Name of Company: | National University of Singapore
| Item | Quantity | Units | Price per unit | Item price
1 | Excavation | 7300 | m3 | 2.9809 | 21760.2383
2 | Gravel bedding | 185 | m3 | 8.5955 | 1590.1713
3 | Concrete for slab | 280 | m3 | 47.8247 | 13390.9159
4 | Concrete for walls | 276 | m3 | 72.7767 | 20086.3738
5 | Reinforcing steel | 836 | kg | 64.0714 | 53563.6634
6 | Backfill | 2800 | m3 | 0.71737 | 2008.6374
|  |  |  | Total bid price | 112400
| Estimated project duration | 61 | calendar days
| Peak manpower requirement | 13 | workers
Particulars of persons making the submission
| Name | MatricNo |  | Signature
1 | Tan Wee Siang | 985804M11
2 | Tan Yan Shin Caleb
Date: